## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 50 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29
|  |  |  | 200 | 193 | 186 | 179 | 172 | 165 | 158 | 151 | 144 | 137 | 130 | 123 | 116 | 109 | 102 | 95 | 88 | 81 | 74 | 67 | 60 | 53 | 46 | 39 | 32 | 25 | 18 | 11 | Ideal Burndown
|  |  | 200 | 200 | 192.5 | 182.5 | 172.5 | 165 | 160 | 155 | 150 | 140 | 128 | 117 | 110 | 105 | 100 | 93 | 85 | 75 | 67 | 62 | 57 | 50 | 45 | 40 | 37 | 31 | 27 | 21 | 15 | Remaining Hrs (Total)
Research game modules | Research | Divya Bharti | 8 | 8 | 6.5 | 4.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research | Uttara Vishwas Kulkarni | 8 | 8 | 6.5 | 4.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research | Arshiya Pathan | 8 | 8 | 6.5 | 4.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research | Shilakha Dawar | 8 | 8 | 6.5 | 4.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research | Divya Thazhathethil | 8 | 8 | 6.5 | 4.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UML Diagram & Documentation | UML Diagram Factory Pattern | Divya Bharti | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UML Diagram Observer Pattern | Uttara Vishwas Kulkarni | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UML Diagram Strategy Pattern | Arshiya Pathan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UML Diagram Chain of Responsibilty Pattern | Shilakha Dawar | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UML Diagram State Pattern | Divya Thazhathethil | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Game Development | Design and Implement Factory Pattern | Divya Bharti | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 25 | 24 | 22 | 21 | 20 | 19 | 17 | 15 | 14 | 13 | 12 | 10 | 9 | 8 | 7 | 6 | 6 | 4 | 3
| Design and Implement Observer Pattern | Uttara Vishwas Kulkarni | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 26 | 23 | 22 | 21 | 20 | 19 | 17 | 15 | 13 | 12 | 11 | 10 | 9 | 8 | 8 | 6 | 5 | 4 | 3
| Design and Implement Strategy Pattern | Arshiya Pathan | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 26 | 24 | 22 | 21 | 20 | 19 | 17 | 15 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 6 | 4 | 3
| Design and Implement Chain of Responsibilty Pattern | Shilakha Dawar | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 25 | 23 | 22 | 21 | 20 | 18 | 17 | 15 | 14 | 13 | 12 | 10 | 9 | 8 | 7 | 7 | 5 | 5 | 3
| Design and Implement State Pattern | Divya Thazhathethil | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 28 | 26 | 23 | 22 | 21 | 20 | 18 | 17 | 15 | 13 | 12 | 11 | 10 | 9 | 8 | 8 | 6 | 5 | 4 | 3
Team:
Divya Bharti | 10 hours / Week
Uttara Vishwas Kulkarni | 10 hours / Week
Arshiya Pathan | 10 hours / Week
Shilakha Dawar | 10 hours / Week
Divya Thazhathethil | 10 hours / Week
Total Available Hours During Sprint: | 200